## Implementation Plan
Project: Baemin_CT HCM, Aug 18th, 2023
To: | FEC
Address:
Task | Deliverable | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Discovery & Planning | Platform Discovery | bar: W1
Access Management Discovery | bar: W1
Operation Integration Discovery | bar: W1
Identity and Access Management Discovery | bar: W2 to W3
Control Tower Design & Deployment | Architecture Design | bar: W3 to W4
Landing Zone Design | bar: W3 to W4
Account Structure and Implementation | bar: W5 to W6
Network & Connect Structure and Implementation | bar: W5 to W7
Shared Services Structure and Implementation | bar: W5 to W7
Security, Governance, and Compliance Implementation | bar: W6 to W8
VPC Structure and Implementation | bar: W6 to W8
Identity and Access Management Config | bar: W6 to W8
Logging and monitoring Implementation | bar: W8 to W9
Tagging | bar: W8 to W9
Migration Wave0 | Control Tower handover | bar: W10
Control Tower testing | bar: W11
Manage Services | Maintain and operate the system and services implemented | bar: W12
Note: All necessary information must be available. Including: compliance requirements, security, platforms, logging & monitoring requirements, application operation process, account strategy

## Implementation Plan MVP
Project: Baemin_CT HCM, Aug 18th, 2023
To: | FEC
Address:
Task | Deliverable | W1 | W2 | W3 | W4
Discovery & Planning | Platform Discovery
Access Management Discovery
Identity and Access Management Discovery
Control Tower Design & Deployment | Architecture Design
Account Structure and Implementation
Network & Connect Structure and Implementation
VPC Structure and Implementation
Identity and Access Management Config
Handover and Testing | Handover and Testing
Note: All necessary information must be available. Including: compliance requirements, security, platforms, logging & monitoring requirements, application operation process, account strategy

## Team
Roles | Manday Rate | Mandays | Total Fee
Project Manager | 320 | 66 | 21120
Security Advisory | 320 | 30 | 9600
Integration Architect | 280 | 44 | 12320
Cloud Architect | 280 | 100 | 28000
Security Architect | 280 | 100 | 28000
Technical Delivery Manager | 320 | 45 | 14400
Network Engineer | 280 | 60 | 16800
Operational Engineer | 280 | 60 | 16800
Devops | 280 | 60 | 16800
Total |  | 565 | 163840

## Team MVP
Roles | Manday Rate | Mandays | Total Fee
Project Manager | 320 | 15 | 4800
Cloud Architect | 280 | 20 | 5600
Network Engineer | 280 | 20 | 5600
Total |  | 55 | 16000

## Role
Role | Role Description
Project Manager/ | Overall program manager and responsible for business communications, delivering strategic oversight to the teams, developing and managing the Project Plan including work streams and sprint cycles.
Quản trị dự án | • Project governance and control
• Detailed project planning and project schedule management
• Run daily standups, status reports (weekly updates), sprint planning, demo and retro sessions
• Financial Management
• Change Management
• Owns resource allocation and scheduling
• Accountable for organization messaging
• Project acceptance and project closure
Quản lý tổng thể và chịu trách nhiệm về truyền thông của dự án, theo dõi & giám sát các thành viên của dự án, phát triển và quản lý Kế hoạch dự án, bao gồm các luồng công việc và chu trình kiểm thử/bàn giao sản phẩm.
• Quản trị và kiểm soát dự án
• Lập kế hoạch dự án chi tiết và quản lý tiến độ dự án
• Chạy standups hàng ngày, báo cáo trạng thái (cập nhật hàng tuần), lập kế hoạch chạy nước rút, các bản demo và các kịch bản bàn giao.
• Quản lý nguồn lực của dự án
• Quản lý sự thay đổi
• Phân bổ và lập kế hoạch tài nguyên
• Chịu trách nhiệm truyền thông trong tổ chức về dự án
• Chấp nhận /nghiệm thu dự án và đóng dự án theo tiến độ.
Integration Architect / Kiến trúc sư tích hợp | Senior technical consultant with expertise in cloud operations and process to manage cloud infrastructure. Functional lead and member of the team that will execute and provide guidance to consultants executing activities related to operations Consultant with experience on deploying operational processes and how to design for cloud operations
Tư vấn kỹ thuật cao cấp, có chuyên môn về vận hành và quy trình hoạt động của đám mây để quản lý cơ sở hạ tầng đám mây. Trưởng nhóm chức năng và các thành viên của nhóm sẽ thực hiện và cung cấp hướng dẫn cho chuyên gia tư vấn thực hiện các hoạt động liên quan. Có kinh nghiệm triển khai các quy trình vận hành và thiết kế tối ưu cho các hoạt động của đám mây
Security Advisory / Chuyên gia tư vấn bảo mật | Consultant with experience on deploying common security frameworks and has the ability to describe the applicability in an AWS environment
Là chuyên gia sẽ review về các chính sách ATTT được triển khai trên hệ thống. Là nhân sự có kinh nghiệm triển khai các khung bảo mật chung và có khả năng mô tả chính xác về cách thức hoạt động của các chính sách bảo mật trong môi trường AWS
Cloud Architect | Responsible for decision making and architecture design and providing overall guidance to technical consultants to troubleshoot and manage challenges identified. Provides in-depth cloud expertise as well as familiarity with application migration methodology for effectiveness at the team level
Chịu trách nhiệm ra quyết định và thiết kế kiến trúc cloud, trực tiếp cấu hình các thành phần dịch vụ & hạ tầng cloud, cung cấp hướng dẫn tổng thể cho để khắc phục sự cố và quản lý các vấn đề được xác định. Có chuyên môn sâu về đám mây cũng như quen thuộc với phương pháp di chuyển ứng dụng để đạt hiệu quả cao nhất.
Security Architect | Define a structured approach to help customers build confidence and trust and enable foundational security, risk and compliance capabilities that accelerate the customer's readiness and planning for a mass migration project addressing security concerns of: Audit, INFOSEC, Risk Management, Legal and Compliance Team.
Xác định cách tiếp cận có cấu trúc để giúp khách hàng xây dựng nền tảng bảo mật chắc chắn & tin cậy. Đảm bảo chắc chắn các khả năng tuân thủ, bảo mật và quản trị rủi ro cơ bản. Giúp tăng độ sẵn sàng của hệ thống và lập kế hoạch cho một dự án đê giải quyết hàng loạt các mối quan tâm về bảo mật như: Kiểm soát, INFOSEC, Quản lý rủi ro, Pháp Chế và Tuân thủ.
Technical Delivery Manager | · Ensure a positive customer onboarding and migration experience
· Support for operation integration engagements
· Project delivery oversight
• Đảm bảo khách hàng hoàn toàn chủ động và nắm chắc về tiến trình dịch chuyển lên đám mây
• Hỗ trợ cho các quá trình tích hợp hoạt động hiệu quả
• Giám sát việc bàn giao dự án
Network Engineer | • Perform networking configurations from FEC's On-Prem to the AWS cloud
• Architecture, division of network layers, network areas on AWS VPCs
• Set up and enforce network access policies, two-way connections of the system
• Operate, maintain, and ensure the operability of AWS cloud networking components
DevOps | Resources to support CI/CD and DevOps activities for the deployment
Hỗ trợ các hoạt động CI / CD và DevOps để triển khai
Có kinh nghiệm và chuyên môn về việc triển khai các môi trường DEV/TEST on AWS
Operation Engineer | Design, develop, test and deploy custom workflows and scripts within the AWS Cloud infrastructure that can be used for integration, deployment, monitoring, compliance, or other ongoing routine IT tasks.
Thiết kế, phát triển, kiểm tra và triển khai các luồng công việc và tập lệnh tùy chỉnh trong cơ sở hạ tầng AWS Cloud có thể được sử dụng để tích hợp, triển khai, giám sát, tuân thủ hoặc các tác vụ CNTT thông thường khác đang diễn ra.

## INF
BẢNG DỰ TOÁN CHI PHÍ DỊCH VỤ AWS
TP. HCM, ngày 21 tháng 7 năm 2023
Kính gửi: CÔNG TY TNHH WOOWA BROTHERS VIỆT NAM
Dụ án: Triển khai Control Tower
STT | Mô tả dịch vụ | Cấu hình | Số lượng | Đơn giá / tháng (USD) | Tổng cộng / tháng (USD) | Tổng cộng / năm (USD) | Đơn giá / tháng (VND) | Tổng cộng / tháng (VND) | Tổng cộng / năm (VND) | 10% | 24200
Tập trung Network Firewall tại Inspection VPC
1 | Virtual Private Cloud
| Number of Transit Gateway attachments | 1 VPC attachment | 1 | 170.5556 | 170.5556 | 2046.6667 | 4586000 | 4586000 | 55032000
| Data processed per Transit Gateway attachment | 5 TB/month
2 | AWS Network Firewall
| AWS Network Firewall Endpoint | Number of Availability Zones that Network Firewall is deployed to: 2 Number of AWS Network Firewall endpoints: 2 Usage per endpoint: 730 | 1 | 640.7778 | 640.7778 | 7689.3333 | 17230000 | 17230000 | 206760000
| AWS Network Firewall Data Processing | Data processed per month: 5 TB/month | 5120 | 0.072222 | 369.7778 | 4437.3333 | 2000 | 10240000 | 122880000
Tập trung inbound traffic
3 | Virtual Private Cloud
| Number of Transit Gateway attachments | 1 VPC attachment | 1 | 125.0444 | 125.0444 | 1500.5333 | 3362000 | 3362000 | 40344000
| Data processed per Transit Gateway attachment | 3 TB/month |  |  |  |  | 0 | 0
4 | AWS Network Firewall
| AWS Network Firewall Endpoint | Number of Availability Zones that Network Firewall is deployed to: 2 Number of AWS Network Firewall endpoints: 2 Usage per endpoint: 730 | 1 | 640.7778 | 640.7778 | 7689.3333 | 17230000 | 17230000 | 206760000
| AWS Network Firewall Data Processing | Data processed per month: 3 TB/month | 3072 | 0.072222 | 221.8667 | 2662.4 | 2000 | 6144000 | 73728000
5 | Elastic Load Balancing
| Number of Application Load Balancers | 1 Application Load Balancer | 1 | 52.8889 | 52.8889 | 634.6667 | 1422000 | 1422000 | 17064000
| Processed bytes (EC2 Instances and IP addresses as targets) | 5 GB/hour
| Average number of new connections per ALB | 5 connections/second
| Average connection duration | 1 seconds
| Average number of requests per second per ALB | 20 requests
6 | AWS Shield
| AWS Shield Standard | AWS Shield Standard | 1 | 0 | 0 | 0 | 0 | 0 | 0
7 | AWS WAF
| Number of Web Access Control Lists (Web ACLs) utilized | 1 | 1 | 212.2222 | 212.2222 | 2546.6667 | 5706000 | 5706000 | 68472000
| Number of Rules added per Web ACL | 100 |  |  |  |  | 0
| Number of Rule Groups per Web ACL | 5 |  |  |  |  | 0
| Number of Rules inside each Rule Group | 10 |  |  |  |  | 0
| Number of Managed Rule Groups per Web ACL | 1 |  |  |  |  | 0
| Number of web requests received across all web ACLs | 50 millions |  |  |  |  | 0
Tập trung outbound traffic
8 | Virtual Private Cloud
| Number of Transit Gateway attachments | 1 VPC attachment | 1 | 79.5333 | 79.5333 | 954.4 | 2139000 | 2139000 | 25668000
| Data processed per Transit Gateway attachment | 1 TB/month |  |  |  |  | 0
| Network Address Translation (NAT) Gateway | Number of NAT Gateways: 2 Data Processed per NAT Gateway: 1 TB/month | 1 | 229.9778 | 229.9778 | 2759.7333 | 6184000 | 6184000 | 74208000
Tập trung VPC endpoint interfaces
9 | Virtual Private Cloud
| Number of Transit Gateway attachments | 1 VPC attachment | 1 | 79.5333 | 79.5333 | 954.4 | 2139000 | 2139000 | 25668000
| Data processed per Transit Gateway attachment | 1 TB/month |  |  |  |  | 0
10 | AWS PrivateLink
| Number of VPC Interface endpoints per AWS region | 5 interfaces | 1 | 105.4667 | 105.4667 | 1265.6 | 2836000 | 2836000 | 34032000
| Number of Availability Zones an Interface endpoint is deployed in | 2 availability zones
| Total data processed by all VPCE Interface endpoints in the AWS region | 2 GB/month
11 | Amazon Route 53
| Hosted Zones | 5 | 1 | 2.8222 | 2.54 | 30.48 | 76000 | 76000 | 912000
| Additional Records in Hosted Zones | 1
| Standard queries | 0,1 million queries/month
Xác thực tập trung SSO
12 | Directory Service
| AD Connector | Total number of directories: 1 AD Connector size: Large | 1 | 194.6667 | 194.6667 | 2336 | 5234000 | 5234000 | 62808000
Lưu trữ log tập trung tại Log Archive account
13 | Amazon S3
| S3 bucket | S3 Standard storage: 100 GB/month PUT, COPY, POST, LIST requests to S3 Standard: 2000000 GET, SELECT, and all other requests from S3 Standard: 10000 Data returned by S3 Select: 10 GB/month | 1 | 13.9 | 13.9 | 166.8 | 374000 | 374000 | 4488000
Security additional
15 | Amazon GuardDuty
| GuardDuty | AWS CloudTrail Management Event Analysis: 1000000 VPC Flow Log Analysis: 20 GB DNS Log Analysis: 2 GB | 1 | 33.2222 | 33.2222 | 398.6667
| TỔNG CỘNG (USD) |  |  |  | 3172.7511 | 38073.0133 |  | 84902000 | 1018824000
*Chi phí trên đã bao gồm các loại thuế theo quy định của pháp luật Việt Nam
digital@techxcorp.com
Level 09, #412 Nguyen Thi Minh Khai, District 3, Ho Chi Minh City
www.techxcorp.com